LIBYAN INTERNATIONAL MEDICAL UNIVERSITY

APPLIED MEDICAL SCIENCES –THIRD YEAR

P.T.S. BLOCK

Assignment

Project management workshop

Name : Mariam Mahmoud Altarhouni	           Student number : 2405

- Develop a network diagram for the project specified below. (50 %)

- Identify the Critical Activities and the total duration of the project. (35%)

- Justify which activity would you crash based on some rationale (15%)

6 d

4 d

D

B

A

4 d

5 d

3 d

5 d

F

E

C

answer 1 :

answer 2:

path 1 : A – B –D-F :19 days

path 2 : A-C-E-F :17 days

path 1 is the critical path because it requires the longest duration.

-if we took the critical path the time will be spent is 19 days.

-If we took the path2 the time will be spent is 17 days

- all the activities require 27 days.

Answer3 :

The activity that would be crashed it is the longest duration , lowest cost , and included in the critical path so it would be D